## Capex
Capital Expenditure
S. No. | Particulars | Scheme Value | Capital Expenditure till 31.03.2025 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
I | Ongoing Schemes
A | Ongoing JUSNL
1 | Transmission Lines | 52.38 | 45.993 | 6.78 | 0 | 0 | 0 | 0 | 0
2 | Substation | 66.85 | 63.01 | 3.84 | 0 | 0 | 0 | 0 | 0
3 | Bays |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | 119.23 | 109.003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | DVC
1 | Transmission Lines | 659.54 | 325.18 | 44.37 | 160.14 | 129.85 | 0 | 0 | 0
2 | Substation | 424.36 | 292.27 | 18.39 | 65 | 48.7 | 0 | 0 | 0
| Total | 1083.9 | 617.45 | 62.76 | 225.14 | 178.55 | 0 | 0 | 0
C | PGCIL (Balance Schemes)
1 | Transmission Lines | 199.05 | 139.335 | 59.715 | 0 | 0 | 0 | 0 | 0
2 | Substations |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | 199.05 | 139.335 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
D | World Bank
1 | Transmission Lines | 934.632 | 0 | 133.6394 | 178.12 | 221.6196 | 0 | 0 | 0
2 | Substation | 1197.065 | 0 | 196.18 | 160.506 | 118.136 | 0 | 0 | 0
| Total | 2131.697 | 0 | 329.8194 | 338.626 | 339.7556 | 0 | 0 | 0
E | Business Plan FY 22-26
1 | Capex Schemes | 1178.1273 | 480.112 | 134.5011 | 368.6039 | 194.9103 | 0 | 0 | 0
| Total | 1178.1273 | 480.112 | 134.5011 | 368.6039 | 194.9103 | 0 | 0 | 0
II | Planned Schemes
F | Planned Schemes
1 | Capex Schemes | 7652.4656 | 0 | 0 | 1540.032 | 2135.9706 | 2063.016 | 1416.697 | 274.33
| Total | 7652.4656 | 0 | 0 | 1540.032 | 2135.9706 | 2063.016 | 1416.697 | 274.33
G | Augmentation Schemes
1 | Schemes | 746.33 | 0 | 0 | 20 | 138.53 | 262.52 | 253.04 | 40.74
| Total | 746.33 | 0 | 0 | 20 | 138.53 | 262.52 | 253.04 | 40.74
H | Grand Total | 13110.7999 | 1345.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Capitalization
S. No. | Particulars | Scheme Value | Capitalization till 31.03.2025 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
I | Ongoing Schemes
A | Ongoing JUSNL
1 | Transmission Lines | 52.38 | 0 | 52.38 | 0 | 0 | 0 | 0 | 0
2 | Substation | 66.85 | 0 | 66.85 | 0 | 0 | 0 | 0 | 0
3 | Bays |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | 119.23 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
B | DVC
1 | Transmission Lines | 659.54 | 0 | 23.06 | 271.05 | 365.43 | 0 | 0 | 0
2 | Substation | 424.36 | 0 | 283.14 | 0 | 141.22 | 0 | 0 | 0
| Total | 1083.9 | 0 | 306.2 | 271.05 | 506.65 | 0 | 0 | 0
C | PGCIL (Balance Schemes)
1 | Transmission Lines | 199.05 | 0 | 199.05 | 0 | 0 | 0 | 0 | 0
2 | Substation |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total | 199.05 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
D | World Bank
1 | Transmission Lines | 934.632 | 0 | 37.8794 | 346.606 | 550.1466 | 0 | 0 | 0
2 | Substation | 1197.065 | 0 | 531.314 | 280.571 | 385.18 | 0 | 0 | 0
| Total | 2131.697 | 0 | 569.1934 | 627.177 | 935.3266 | 0 | 0 | 0
E | Business Plan FY 22-26
1 | Capex Schemes | 1178.1273 | 0 | 148.9973 | 619.61 | 409.52 | 0 | 0 | 0
| Total | 1178.1273 | 0 | 148.9973 | 619.61 | 409.52 | 0 | 0 | 0
| Grand Total | 4712.0043 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
II | Planned Schemes
F | Planned Schemes
1 | Capex Schemes | 7652.4656 | 0 | 0 | 0 | 2785.4826 | 2198.806 | 2081.427 | 414.33
| Total | 7652.4656 | 0 | 0 | 0 | 2785.4826 | 2198.806 | 2081.427 | 414.33
G | Augmentation Schemes
1 | Schemes | 746.33 | 0 | 0 | 0 | 98.53 | 202.52 | 353.04 | 35.74
| Total | 746.33 | 0 | 0 | 0 | 98.53 | 202.52 | 353.04 | 35.74
H | Grand Total | 13110.7999 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8398.7956
8393.7956
1678.7591
| Capital Expenditure | [8 empty] | 3357518.2426
S. No. | Particulars | Scheme Value | Capital Expenditure till 31.03.2025 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | 3362518.2426
1 | Ongoing Schemes | 4712.0043 | 1345.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Planned Schemes | 7652.4656 | 0 | 0 | 1540.032 | 2135.9706 | 2063.016 | 1416.697 | 274.33
3 | Augmentation | 746.33 | 0 | 0 | 20 | 138.53 | 262.52 | 253.04 | 40.74
| Total | 13110.7999 | 1345.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Capital Expenditure
S. No. | Particulars | Scheme Value | Capital Expenditure till 31.03.2023 | FY 2023-24
1 | Ongoing Schemes | 3533.877 | 865.788 | #REF!
2 | Planned Schemes | 7652.4656 | 0 | 0
3 | Augmentation | 746.33 | 0 | 0
4 | Renovation & Modernization |  | #REF! | #REF!
| Total | 11932.6726 | #REF! | #REF!
Capitalization
S. No. | Particulars | Scheme Value | FY 2023-24
1 | Ongoing Schemes | 3533.877 | #REF!
2 | Planned Schemes | 7652.4656 | 0
3 | Augmentation | 746.33 | 0
4 | Renovation & Modernization | 0 | #REF!
| Total | 11932.6726 | #REF!
S. No. | Particulars | Scheme Value | FY 2021-22 | FY 2022-23 | FY 2023-24 | FY 2024-25 | FY 2025-26
1 | Planned Schemes | 7652.4656 | 0 | 0 | 0 | 99.1544 | 1083.86
2 | Augmentation | 746.33 | 0 | 0 | 0 | 746.33 | 0
| Total | 8398.7956 | 0 | 0 | 0 | 845.4845 | 1083.86
Capitalization
S. No. | Particulars | Scheme Value | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
1 | Ongoing Schemes | 4712.0043 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Planned Schemes | 7652.4656 | 0 | 0 | 2785.4826 | 2198.806 | 2081.427 | 414.33
3 | Augmentation | 746.33 | 0 | 0 | 98.53 | 202.52 | 353.04 | 35.74
| Total | 13110.7999 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Transmission state work
TRANSMISSION LINES | Length (In KM) | In CKM | Project Commencement | Total Awarded Value in Rs. Crs. | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs.
State Funded | [5 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
[10 empty] | Projected | Actual
132KV Garhwa - Japla transmission line | 35.73 | 71.46 | 2012-12-21 | 28.35 | 21.57 | 100% | [5 empty] | 6.78 | [6 empty] | 28.35
Total | 35.73 | 71.46 |  | 28.35 | 21.57 |  |  |  |  | 0 | 0 | 6.78 | 0 | 0 | 0 | 0 | 0 | 0 | 28.35 | 0 | 0 | 0 | 0 | 0
220 kV Transmission Line(Planned Projects)
LILO of 220 KV D/C TTPS-Govindpur transmission line at Jainamore Bokaro | 24 | 48 | 2017-04-04 | 24.03 | 24.423 | [5 empty] | 0 | 0 | [6 empty] | 24.03
Total | 24 | 48 |  | 24.03 | 24.423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.03 | 0 | 0 | 0 | 0 | 0
Grand Total | 59.73 | 119.46 |  | 52.38 | 45.993 | 0 | 0 | 0 | 0 | 0 | 0 | 6.78 | 0 | 0 | 0 | 0 | 0 | 0 | 52.38 | 0 | 0 | 0 | 0 | 0

## GSS State funded work
Name of GSS | Capacity Addition (In MVA) | Project Commencement | Total Awarded Value in Rs. Crs. | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs.
State Funded |  |  |  |  | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
[9 empty] | Projected | Actual
220/132/33 KV Grid Substation (Ongoing Projects)
220/132/33KV Grid Sub-Station Bokaro (jainamore) 2x150 MVA+2x50 MVA, | 400 | 2016-05-17 | 66.85 | 63.01 | [6 empty] | 3.84 | [6 empty] | 66.85
Total | 400 |  | 66.85 | 63.01 |  |  |  |  | 0 | 0 | 3.84 | 0 |  |  |  |  | 0 | 66.85 | 0 | 0 | 0 | 0 | 0
Grand Total | 400 |  | 66.85 | 63.01 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 0 | 0 | 0 | 0 | 0 | 0 | 66.85 | 0 | 0 | 0 | 0 | 0

## Line DVC
TRANSMISSION LINES | Length (In KM) | In CKM | Project Commencement | Total Awarded Value in Rs. Crs. | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs.
132 kV Transmission Line(Ongoing Projects)-DVC | [5 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
[10 empty] | Projected | Actual
132 KV D/C Ramgarh-Hazaribagh | 43 | 86 | 2018-11-01 | 19.88 | 6.95 | 100% | 0 |  |  |  |  | 9 | 3.93 | [6 empty] | 19.88
132 KV D/C Ramgarh-Gola | 37 | 74 | 2019-02-21 | 21.46 | 15.12 | 100% | 0 |  |  |  |  | 5 | 1.34 | [6 empty] | 21.46
132 KV D/C Gola-Peterwar | 16 | 32 | 2018-11-01 | 31.99 | 18.32 | 100% | 0 |  |  |  |  | 3 | 10.67 | [6 empty] | 31.99
132 kV D/C 3 Ph. Peterwar - Jaina More (Bokaro) Transmission line | 23 | 46 | 2018-11-01 |  |  | 100% | 0
132 KV D/C Nirsa-Baliyapur | 24 | 48 | 2019-02-21 | 13.13 | 11.43 | 100% | 0 |  |  |  |  | 1.7 | [6 empty] | 13.13
132 kV D/C 3 Ph. Ramgarh - PTPS Transmission line | 20 | 40 | 2018-11-01 | 93.97 | 2.02 | 100% | 0 |  |  |  |  | 10 | 40 | 41.95 | [6 empty] | 93.97
132 kV D/C 3 Ph. Barkagaon - PTPS (220 kV) Transmission line | 32 | 64 | 2018-07-24 | 20.12 | 14.34 | 100% | 0 | [5 empty] | 2 | 3.78 | [6 empty] | 20.12
132 kV D/C 3 Ph. Silli - Gola Transmission line | 26 | 52 | 2019-02-21 | 28.71 | 22.3 | 100% | 0 |  |  |  |  | 2 | 4.41 | [6 empty] | 28.71
132 kV D/C 3 Ph. Chandankyari - Govindpur Transmission line LILO at Putki | 33 | 66 | 2019-02-21 | 18.79 | 14.64 | 100% | 0 |  |  |  |  | 3.5 | 0.65 | [6 empty] | 18.79
132 kV D/C 3 Ph. Chandankyari - Bokaro(Jaina more) transmission line LILO at Dugda | 22 | 44 | 2019-02-21 | 24.82 | 21.95 | 100% | 0 |  |  |  |  | 2.5 | 0.37 | [6 empty] | 24.82
132 kV D/C 3 Ph. Mahuda - Putki Transmission line | 9 | 18 | 2019-02-21 | 9.93 | 8.76 | 100% | 0 |  |  |  |  | 1.17 | [6 empty] | 9.93
132 kV D/C 3 Ph. Gomia - Dugda Transmission line | 50 | 100 | 2019-02-21 | 54.13 | 34.36 | 100% | 0 |  |  |  |  | 2 | 10 | 7.77 | [6 empty] | 54.13
132 kV D/C 3 Ph. Barhi - Chatra Transmission line | 34 | 68 | 2018-11-01 | 18.89 | 17.94 | 100% | 0 |  |  | 0.15 |  | 0 | 0.95 | [6 empty] | 18.89
132 kV D/C 3 Ph. Bishnugarh - Hazaribagh Transmission line | 47 | 94 | 2018-11-01 | 20.94 | 6.92 | 100% | 0 | [5 empty] | 8 | 6.02 | [6 empty] | 20.94
132 kV D/C 3 Ph. Saria - Bishnugarh Transmission line | 26 | 52 | 2018-11-01 | 20.45 | 15.85 | 100% | 0 |  |  | 0.16 |  | 1 | 3.6 | [6 empty] | 20.45
132 kV D/C 3 Ph. Gomia - Bishnugarh Transmission line | 21 | 42 | 2018-11-01 | 99.68 | 3.52 | 100% | 0 | [5 empty] | 40 | 56.16 | [6 empty] | 99.68
132 kV D/C 3 Ph. Chatra-Simaria | 28 | 56 | 2019-02-21 | 25.73 | 19.76 | 100% | 0 |  |  |  |  | 1 | 4.97 | [6 empty] | 25.73
132 kV D/C 3 Ph. Barhi - Hazaribagh (220 kV) Transmission line | 42 | 84 | 2018-11-01 | 18.49 | 5.33 | 100% | 0 | [5 empty] | 5 | 8.16 | [6 empty] | 18.49
132 kV D/C 3 Ph.Jamua- Gawan Transmission line | 58 | 116 | 2018-11-01 | 33.97 | 29.33 | 100% | 0 |  |  |  |  | 0.5 | 4.14 | [6 empty] | 33.97
132 kV D/C 3 Ph. Koderma- Gawan Transmission line | 54 | 108 | 2018-11-01 | 26.36 | 14.25 | 100% | 0 |  |  | 1.5 |  | 2 | 10.11 | [6 empty] | 26.36
132 kV D/C Hunterganj-Itkhori Transmission line | 54 | 108 | 2018-11-01 | 40.03 | 29.16 | 100% | 0 |  |  | 0 |  |  | 5 | 5.87 | [6 empty] | 40.03
132 kV D/C Hunterganj-Chatra Transmission line | 30 | 60 | 2018-11-01 | 18.07 | 12.93 | 100% | 0 |  |  | 0 |  |  | 5 | 0.14 | [6 empty] | 18.07
Total | 729 | 1458 |  | 659.54 | 325.18 |  |  |  |  | 1.81 | 0 | 44.37 | 160.14 | 129.85 | 0 | 0 | 0 | 0 | 23.06 | 271.05 | 365.43 | 0 | 0 | 0

## GSS DVC
Name of GSS | Capacity Addition (In MVA) | Project Commencement | Total Awarded Value in Rs. Crs. | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs.
[5 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
132/33 KV GSS-DVC | [8 empty] | Projected | Actual
132/33 KV GSS Nirsa(2x50 MVA) | 100 | 2019-02-21 | 26.59 | 25.28 | 100% | 0 |  |  |  |  | 1.31 | [6 empty] | 26.59
132/33 kV GSS at Ramgarh(2x50 MVA) | 100 | 2018-11-01 | 36.22 | 13.66 | 100% | 0 |  |  |  |  | 0 | 14 | 8.56 | [6 empty] | 36.22
132/33 kV GSS at Petarwar(2x50 MVA) | 100 | 2018-11-01 | 48.42 | 45.94 | 100% | 0 |  |  |  |  | 2.48 | [6 empty] | 48.42
132/33 kV GSS at Barkagaon (2x50 MVA) | 100 | 2018-07-24 | 33.71 | 0 | 100% | 0 | [5 empty] | 17 | 16.71 | [6 empty] | 33.71
132/33 kV GSS at Gola (2x50 MVA) | 100 | 2019-02-21 | 26.72 | 24.12 | 100% | 0 |  |  |  |  | 2.6 | [6 empty] | 26.72
132/33 kV GSS at Barhi (2 x 50 MVA) | 100 | 2018-11-01 | 36.74 | 13.86 | 100% | 0 | [5 empty] | 14 | 8.88 | [6 empty] | 36.74
132/33 kV GSS at Dugda (2 x 50 MVA) | 100 | 2019-02-21 | 23.56 | 22.62 | 100% | 0 |  |  |  |  | 0.94 | [6 empty] | 23.56
132/33 kV GSS at Putki (2 x 50 MVA) | 100 | 2019-02-21 | 26.66 | 25.81 | 100% | 0 |  |  |  |  | 0.85 | [6 empty] | 26.66
132/33 kV GSS at Mahuda (2 x 50 MVA) | 100 | 2019-02-21 | 28.85 | 26.81 | 100% | 0 |  |  |  |  | 2.04 | [6 empty] | 28.85
132/33 kV GSS at Bishnugarh (2 x 50 MVA) | 100 | 2018-11-01 | 37.55 | 35.17 | 100% | 0 |  |  |  |  | 2.38 | [6 empty] | 37.55
132/33 KV GSS Simaria (2 x 50 MVA) | 100 | 2019-02-21 | 29.55 | 26.69 | 100% | 0 |  |  |  |  | 2.86 | [6 empty] | 29.55
132/33kV GSS at Gawan (2x50 MVA) | 100 | 2018-11-01 | 35.24 | 32.31 | 100% | 0 |  |  |  |  | 2.93 | [6 empty] | 35.24
132/33kV GSS at Hunterganj (2x50 MVA) | 100 | 2018-11-01 | 34.55 | 0 | 100% | 0 | [5 empty] | 20 | 14.55 | [6 empty] | 34.55
Total | 1300 |  | 424.36 | 292.27 |  |  |  |  | 0 | 0 | 18.39 | 65 | 48.7 | 0 | 0 | 0 | 0 | 283.14 | 0 | 141.22 | 0 | 0 | 0

## Line_PGCIl
TRANSMISSION LINES | Length (In KM) | In CKM | Project Commencement | Total Awarded Value in Rs. Crs. | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs.
PGCIL | [5 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
[10 empty] | Projected | Actual
400 kV Transmission Line(Ongoing Projects)
400 KV D/C Latehar(JSEB) to 400 KV PTPS G/S/S | 107.507 | 215.014 | 2012-10-17 | 199.05 | 139.335 | 100% | 0 |  |  |  |  | 59.715 | [6 empty] | 199.05
Total | 107.507 | 215.014 |  | 199.05 | 139.335 |  |  |  |  | 0 | 0 | 59.715 | 0 | 0 | 0 | 0 | 0 | 0 | 199.05 | 0 | 0 | 0 | 0 | 0
Grand Total | 107.507 | 215.014 | 0 | 199.05 | 139.335 | 0 | 0 | 0 | 0 | 0 | 0 | 59.715 | 0 | 0 | 0 | 0 | 0 | 0 | 199.05 | 0 | 0 | 0 | 0 | 0

## WB-L
| TRANSMISSION LINES | Pkg | Length (In KM) | In CKM | Project Commencement | Total Awarded Value in Rs. (with GST) | Expenditure incurred till 31.03.2025 in Rs. Crs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs. | [6 empty] | Package
| 132 kV D/C 3 Ph- Transmission Line-World bank funded | [6 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
[12 empty] | Projected | Actual
132 kV Transmission Line(Planned Projects)
Package No. 01B | 132 kV D/C 3 Ph. Silli - Angada Transmission line | 01B | 39.05 | 78.1 | 21.01.2019 |  |  | 70% | 30% | [17 empty] | 01B
| 132 kV D/C 3 Ph. Silli - Chouka Transmission line | 01B | 52.19 | 104.38 | 21.01.2019 |  |  | 70% | 30% | [17 empty] | 01B
| 132 kV D/C 3 Ph. Irba - Kanke Transmission line | 01B | 22.6 | 45.2 | 21.01.2019 |  |  | 70% | 30% | [17 empty] | 01B
| 132 kV D/C 3 Ph. Irba - Ratu Transmission line | 01B | 42.68 | 85.36 | 21.01.2019 |  |  | 70% | 30% | [17 empty] | 01B
| 132 kV D/C 3 Ph. Angada - Sikidiri (Irba) Transmission line | 01B | 34.53 | 69.06 | 21.01.2019 |  |  | 70% | 30% | [17 empty] | 01B
[6 empty] | 136.0073 | 24.807 | 70% | 30% |  |  | 0 |  | 15 | 15 | 81.2003 | [6 empty] | 136.0073
Package No. 02B | 132 kV D/C 3 Ph. Dumka - Sikaripara Transmission line | 02B | 51.28 | 102.56 | 10.01.2019 |  |  | 70% | 30% | [17 empty] | 02B
| LILO of 132 kV D/C 3 Ph. Dumka-Deoghar Transmission line at GSS Jarmundi | 02B | 3.69 | 7.38 | 10.01.2019 |  |  | 70% | 30% | [17 empty] | 02B
| 132 kV D/C 3 Ph. Amrapara - Godda Transmission line | 02B | 67.45 | 134.9 | 10.01.2019 |  |  | 70% | 30% | [17 empty] | 02B
| 132 kV D/C 3 Ph. Amrapara - Pakur Transmission line | 02B | 24.73 | 49.46 | 10.01.2019 |  |  | 70% | 30% | [17 empty] | 02B
[6 empty] | 112.7113 | 28.444 | 70% | 30% |  |  | 0 |  | 15 | 10 | 59.2673 | [6 empty] | 112.7113
Package No. 03B | 132 kV D/C 3 Ph. Naudiha - Chatarpur Transmission line | 03B | 18.49 | 36.98 | 11.01.2019 |  |  | 70% | 30% | [17 empty] | 03B
| 132 kV D/C 3 Ph. Nagar Utari - Garhwa(220KV) Transmission line | 03B | 15.85 | 31.7 | 11.01.2019 |  |  | 70% | 30% | [17 empty] | 03B
[6 empty] | 37.8794 | 18.24 | 70% | 30% |  |  | 0 |  | 19.6394 | [6 empty] | 37.8794
Package No. 04B | 132 kV D/C 3 phase Surda - Jadugoda transmission line | 04B | 20.82 | 41.64 | 14.02.2019 |  |  | 70% | 30% | [17 empty] | 04B
| 132 kV D/C 3 phase Surda - Bharagora transmission line | 04B | 43.4 | 86.8 | 14.02.2019 |  |  | 70% | 30% | [17 empty] | 04B
| LILO 1 & 2 of 132 kV D/C 3 Ph. Ramchandarpur-Jadugoda Transmission line at GSS Sundarnagar | 04B | 35.11 | 70.22 | 14.02.2019 |  |  | 70% | 30% | [17 empty] | 04B
| LILO 1 & 2 of 132 kV D/C 3 Ph. Baharagora-Dalbhumgarh Transmission line at GSS Chaukliya | 04B | 42.58 | 85.16 | 14.02.2019 |  |  | 70% | 30% | [17 empty] | 04B
[6 empty] | 90.5782 | 24.58 | 70% | 30% |  |  | 0 |  | 20 | 26 | 19.9982 | [6 empty] | 90.5782
Package No. 05B | LILO of one Ckt Of 132 KV D/C 3 ph Chaibasa- Manoharpur Transmission Line at132/33 KV GS/S at Goelkera including with 2 nos. of 132 kV bay. | 05B | 2.8 | 5.6 | 10.12.2019 |  |  | 70% | 30% | [17 empty] | 05B
| 132 kV D/C 3 Ph. Chauka - Tamar Transmission line | 05B | 27.61 | 55.22 | 10.12.2019 |  |  | 70% | 30% | [17 empty] | 05B
| LILO 132 kV S/C 3 Ph. Chandil -Rajkharsawan line at kandra . | 05B | 2.62 | 5.24 | 10.12.2019 |  |  | 70% | 30% | [17 empty] | 05B
[6 empty] | 25.167 | 16.971 | 70% | 30% |  |  |  |  | 4 | 4.196 | [6 empty] | 25.167
Package No. 06B | LILO of 132 kV Dumka - Lalmatia transmission line at GSS Hansdiha | 06B | 3.42 | 6.84 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 06B
| 132 kV D/C 3 Ph. Sarath - Palajori Transmission line | 06B | 20.1 | 40.2 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 06B
| 132 kV D/C 3 Ph. Sarath - chitra Transmission line | 06B | 15.14 | 30.28 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 06B
| LILO 1&2 of 132 kV D/C 3 Ph. jamtara-Madhupur Transmission line at GSS Naranpur | 06B | 25.95 | 51.9 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 06B
| Hansdiah-Jasidih | 06B | 45.4 | 90.8 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 06B
[6 empty] | 76.594 | 58.048 | 70% | 30% |  |  |  |  | 5 | 13.546 | [6 empty] | 76.594
Package No. 07B | 132 kV D/C 3 phase Kurdeg -simdega transmission line | 07B | 35.85 | 71.7 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 07B
| 132 kV D/C 3 Ph. Chainpur-Mahuadanr Transmission line | 07B | 53.64 | 107.28 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 07B
| LILO 132 kV D/C 3 Ph. Gumla - Simdega Transmission line at chainpur | 07B | 35.68 | 71.36 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 07B
| 132 kV D/C 3 phase Kolebira -Kamdara transmission line | 07B | 38.66 | 77.32 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 07B
| 132 kV D/C 3 phase Kolebira -simdega transmission line | 07B | 16.4 | 32.8 | 31.01.2020 |  |  | 70% | 30% | [17 empty] | 07B
[6 empty] | 109.807 | 85.217 | 70% | 30% |  |  |  |  | 20 | 4.59 | [6 empty] | 109.807
Package No. 08B | 132 kV D/C 3 Ph. Chhatarpur - Daltonganj 220 kV Transmission line | 08B | 34.41 | 68.82 | 22.10.2019 |  |  | 70% | 30% | [17 empty] | 08B
| 132 kV D/C 3 Ph. Chhatarpur - Japla Transmission line | 08B | 35.8 | 71.6 | 22.10.2019 |  |  | 70% | 30% | [17 empty] | 08B
| 132 kV D/C 3 Ph. Chandwa - Latehar Transmission line | 08B | 23.46 | 46.92 | 22.10.2019 |  |  | 70% | 30% | [17 empty] | 08B
| 132 kV D/C 3 Ph. Chhatarpur - Panki Transmission line | 08B | 65.39 | 130.78 | 22.10.2019 |  |  | 70% | 30% | [17 empty] | 08B
| 132 kV D/C 3 Ph. Ramkanda - Garhwa (220KV) Transmission line | 08B | 52.09 | 104.18 | 22.10.2019 |  |  | 70% | 30% | [17 empty] | 08B
[6 empty] | 135.038 | 104.25 | [6 empty] | 10 | 20.788 | [6 empty] | 135.038
95.4 | Design, Engineering, Supply, Erection, Testing and Commissioning of 220 kV D/C Transmission Line Chandil (New) – Jadugoda (New) (51.3KM), 220 kV D/C Transmission Line Chaibasa (PGCIL) –Jadugoda (New)( 47.7 KM). (Package 10B1) |  | 99 | 198 |  | 135.067 | 16.466 | [6 empty] | 20 | 60 | 38.601 | [6 empty] | 135.067
126.8 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 kV D/C Transmission Line Jadugoda (New) – Dhalbhumgarh (63.4KM). |  | 63.4 | 126.8 |  | 75.7828 | 24.23 | [6 empty] | 5 | 24 | 22.5528 | [6 empty] | 75.7828
| Total |  | 1211.27 | 2422.54 | 0 | 934.632 | 401.253 | 28 | 12 | 0 | 0 | 0 | 0 | 133.6394 | 178.12 | 221.6196 | 0 | 0 | 0 | 0 | 37.8794 | 346.606 | 550.1466 | 0 | 0 | 0

## WB_GSS
Name of Package | Name of GSS | Capacity Addition (In MVA) | Project Commencement | Total Awarded Value in Rs. (with GST) | Expenditure incurred till 31.03.2025 in Rs. | Funding Pattern in percentage |  |  |  | Capital Expenditure in Rs. Crs. | [7 empty] | Capitalization in Rs. Crs. | [6 empty] | Package
[6 empty] | Debt | Equity | Grant | Consumer Contribution | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
| 132/33 KV Grid Substation (Planned Projects)-World Bank funded | [8 empty] | Projected | Actual
Package No. 02A | 132/33 kV GSS at Sikaripara(2x50 MVA) | 100 | 22.02.2019 |  |  | 70% | 30% | [17 empty] | 02A
| 132/33 kV GSS at Jarmundi(2x50 MVA) | 100 | 22.02.2019 |  |  | 70% | 30% | [17 empty] | 02A
| 132/33 kV GSS at Amarpara(2x50 MVA) | 100 | 22.02.2019 |  |  | 70% | 30% | [17 empty] | 02A
| Pakur bay Extn |  | 22.02.2019 |  |  | 70% | 30% | [17 empty] | 02A
|  |  |  | 127.305 | 125.937 | 70% | 30% |  |  |  |  | 1.368 | [6 empty] | 127.305
Package No. 01A | 132/33 kV GSS at Irba(2x50 MVA) | 100 | 30.01.2019 |  |  | 70% | 30% | [17 empty] | 01A
| 132/33 kV GSS at Angada(2x50 MVA) | 100 | 30.01.2019 |  |  | 70% | 30% | [17 empty] | 01A
| 132/33 kV GSS at Kanke Bay Extn (2x50 MVA) | 100 | 30.01.2019 |  |  | 70% | 30% | [17 empty] | 01A
| 132/33 kV GSS at Silli (2x50 MVA) | 100 | 30.01.2019 |  |  | 70% | 30% | [17 empty] | 01A
|  |  |  | 148.254 | 147.062 | 70% | 30% |  |  |  |  | 1.192 | [6 empty] | 148.254
Package No. 04A | 132/33 kV GSS at Chatarpur (2 x 50 MVA) | 100 | 18.12.2020 |  |  | 70% | 30% | [17 empty] | 04A
| 132/33 kV GSS at Sundarnagar (2x50 MVA) | 100 | 18.12.2020 |  |  | 70% | 30% | [17 empty] | 04A
| 132/33 kV GSS at Sarath (2x50 MVA) | 100 | 18.12.2020 |  |  | 70% | 30% | [17 empty] | 04A
|  |  |  | 164.26 | 39.484 | 70% | 30% |  |  |  |  | 30 | 30 | 64.776 | [6 empty] | 164.26
Package No. 08A | Japla GSS Bay Extn |  | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 08A
| 132/33KV GSS Ramkanda(2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 08A
| 132/33KV GSS Panki(2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 08A
| 132/33 kV GSS at Chandwa (2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 08A
|  |  |  | 118.97 | 77.56 | 70% | 30% |  |  |  |  | 10 | 20 | 11.41 | [6 empty] | 118.97
Package No. 03A | 132/33KV GSS NagarUntari(2x50 MVA) | 100 | 15.03.2019 |  |  | 70% | 30% | [17 empty] | 03A
| 132/33KV GSS Meral(2x50 MVA) | 100 | 15.03.2019 |  |  | 70% | 30% | [17 empty] | 03A
| 132/33KV GSS Mahuadanr(2x50 MVA) | 100 | 15.03.2019 |  |  | 70% | 30% | [17 empty] | 03A
| 132/33KV GSS Naudiha(2x50 MVA) | 100 | 15.03.2019 |  |  | 70% | 30% | [17 empty] | 03A
|  |  |  | 163.391 | 123.15 | 70% | 30% |  |  |  |  | 40.241 | [6 empty] | 163.391
Package No. 05A | Goielkera GSS bay Extn |  | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
| Kandra GSS(2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
| Musabani Bay Extn |  | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
| 132/33 kV GSS at Chouka(2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
| 132/33 kV GSS at Surda 2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
| 132/33 kV GSS at Chakuliya(2x50 MVA) | 100 | 29.08.2019 |  |  | 70% | 30% | [17 empty] | 05A
|  |  |  | 165.117 | 124.477 | 70% | 30% |  |  |  |  | 36 | 4.64 | [6 empty] | 165.117
Package No. 06A | 132/33 kV GSS at Hansdiha (2x50 MVA) | 100 | 14.11.2019 |  |  | 70% | 30% | [17 empty] | 06A
| 132/33 kV GSS at Narayanpur(2x50 MVA) | 100 | 14.11.2019 |  |  | 70% | 30% | [17 empty] | 06A
|  |  |  | 76.206 | 30.497 | 70% | 30% |  |  |  |  | 45.709 | [6 empty] | 76.206
Package No. 07A | 132/33 kV GSS at Chainpur (2x50 MVA) | 100 | 30.09.2020 |  |  | 70% | 30% | [17 empty] | 07A
| 132/33 kV GSS at Koleibera(2x50 MVA) | 100 | 30.09.2020 |  |  | 70% | 30% | [17 empty] | 07A
| 132/33 kV GSS at Kurdeg(2x50 MVA) | 100 | 30.09.2020 |  |  | 70% | 30% | [17 empty] | 07A
| Kamdara GSS Bay Extn. |  | 30.09.2020 |  |  | 70% | 30% | [17 empty] | 07A
|  |  |  | 115.454 | 44.588 | [6 empty] | 15 | 55.866 | [6 empty] | 115.454
Package 09 | Bay Extension at 220/132kV GSS Jasidih, 132/33kV GSS Chitra, 132/33kV GSS Simdega,132/33kV GSS Latehar (Awarded on 23 Jan 2024, C Ag No-4) |  |  | 16.158 | 9.488 | [6 empty] | 6.67 | [6 empty] | 16.158
| Design, Engineering, Supply, Erection, Testing and Commissioning of 2x200 MVA, 220/132 kV Grid Sub Station (AIS) at Jadugoda (New) (220 KV - TRF Bay-02 Nos. Line Bay- 04 nos. B/C-01 nos. Bus Transfer Bay-01 Nos, 132 KV- TRF Bay-02 Nos, Line Bay-04 Nos, Transfer Bus coupler Bay-01 Nos) & 02 Nos of 132 Bay at 132/33 kV Grid Sub Station Dhalbhumgarh (Existing) with dismantling work for 02 Nos 132 KV Bay and 33 KV Bay Sub Station. | 400 |  | 101.95 | 0 | [6 empty] | 10 | 50 | 41.95 | [6 empty] | 101.95
| Total | 3000 |  | 1197.065 | 722.243 | 26.6 | 11.4 | 0 | 0 | 0 | 0 | 196.18 | 160.506 | 118.136 | 0 | 0 | 0 | 0 | 531.314 | 280.571 | 385.18 | 0 | 0 | 0

## Business Plan FY 22-26
Supplementary Revised Business Plan for State Funded Planned Projects
Sl No. | Project | Estimated Amount (in Cr.) |  | Capital Expenditure Schedule | [7 empty] | Capitalization Schedule
|  |  | Expenditure incurred till 31.03.2025 in Rs. | FY 2024-25 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2024-25 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
|  |  |  | Projected | Actual
1 | 220/132/33 kV Grid sub-station, Koderma | 43.99 | 2.89 |  |  | 2 | 20 | 19.1 | [6 empty] | 43.99
2 | 220/132/33 kV Grid sub-station, Patratu | 123.3873 | 116.8862 |  |  | 6.5011 | [6 empty] | 123.3873
3 | 132 KV Jamtara - Madhupur Transmission line of propose LILO at Kundhit grid | 25.61 | 25.61 |  |  | 0 | [6 empty] | 25.61
4 | 220/132/33 kV Grid Sub-Station, Hazaribagh | 127.53 | 4.7197 |  |  | 5 | 80 | 37.8103 | [6 empty] | 127.53
5 | 220 KV D/C Tenughat - Hazaribagh Transmission line | 86.96 | 39 |  |  | 20 | 27.96 | [6 empty] | 86.96
6 | 220/132/33 KV Grid Sub Station, Baliyapur | 131.82 | 91.7642 |  |  | 30 | 10.0558 | [6 empty] | 131.82
7 | LILO of 220 KV D/C Dumka - Govindpur at Baliyapur GSS | 42.26 | 19.52 |  |  | 10 | 12.74 | [6 empty] | 42.26
8 | 220 kV Dhanbad (NKTL) – Baliyapur Transmission line | 29.48 | 12.77 |  |  | 10 | 6.71 | [6 empty] | 29.48
9 | 220/132/33 kV, 2x200+2x80 MVA GSS, Gomia Grid Sub-station | 131.82 | 64.569 |  |  | 20 | 47.251 | [6 empty] | 131.82
10 | 220 kV D/C TTPS- Gomia Transmission line | 29.48 | 8.8329 |  |  | 6 | 14.6471 | [6 empty] | 29.48
11 | 220/132/33 kV Bero Grid Sub-station & associated transmisison line | 128 | 0 |  |  |  | 50 | 78 | [6 empty] | 128
12 | 220/132/33 Grid Sub Station, Sarwal & associated trasmission line | 110 | 0 |  |  |  | 50 | 60 | [6 empty] | 110
13 | 220/132/33 Grid Sub Station, Palajori & associated trasmission line | 103 | 91.3 |  |  | 5 | 6.7 | [6 empty] | 103
14 | 132/33 KV GSS, 100 MVA, AIIMS Devipur, Doghar and LILO of 132 KV DC Madhupur Jasidih TL at 132/33 KV Devipur | 64.79 | 2.25 |  |  | 20 | 42.54 | [6 empty] | 64.79
| Total | 1178.1273 | 480.112 | 0 | 0 | 134.5011 | 368.6039 | 194.9103 | 0 | 0 | 0 | 0 | 148.9973 | 619.61 | 409.52 | 0 | 0 | 0

## Business Plan FY 26-31
Business Plan for State Funded Planned Projects
Sl No. | Project | Estimated Amount (in Cr.) | Capital Expenditure Schedule | [6 empty] | Capitalization Schedule
|  |  | FY 2025-26 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
1 | i. Establishment of New 220/132/33 kV, 2x200+2x80 MVA at Sarwal | 138.66 |  |  | 55.464 | 83.196 | [5 empty] | 138.66
2 | ii. LILO of Chandil old – Ranchi (PG) 220 kV Zebra S/c line at Sarwal (36 ckm) | 26.53 |  |  | 10.612 | 15.918 | [5 empty] | 26.53
3 | iii. Sarwal – Khunti 132 kV Panther D/c Line (120 ckm) | 72.39 |  |  | 28.956 | 43.434 | [5 empty] | 72.39
4 | i. Establishment of New 132/33 kV, 2x80 MVA at Mandar | 74.95 |  |  | 20 | 30 | 24.95 | [5 empty] | 74.95
5 | ii. Mandar – Itki 132 kV Zebra D/c Line (20 ckm) | 14.7 |  |  |  | 5 | 9.7 | [5 empty] | 14.7
6 | i. Establishment of New 400/220/132/33 kV, 2x500+2x200+2x80 MVA at Itki | 253.19 |  |  | 100 | 153.19 | [5 empty] | 253.19
7 | ii. LILO of Ranchi New PG – Patratu New 400 kV Twin Moose D/c line at Itki (72ckm) | 114.3 |  |  | 50 | 64.3 | [5 empty] | 114.3
8 | iii. LILO of Hatia – Loherdaga New 220 kV Zebra D/c line at Itki (60ckm) | 44.22 |  |  | 20 | 24.22 | [5 empty] | 44.22
9 | iv. Itki – Khunti 132 kV Panther D/c Line (120ckm) | 72.39 |  |  | 40 | 32.39 | [5 empty] | 72.39
10 | v. Itki – Ranchi Smart City 220 kV Zebra through LILO of Under-Construction Ranchi Smart City- Mandar S/c on D/c line.(20 ckm) | 14.7 |  |  | 5 | 9.7 | [5 empty] | 14.7
11 | i. Establishment of New 132/33 kV, 2x80 MVA at Ghagra (Gumla) | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
12 | ii. Lohardaga (New) – Ghagra 132 kV Panther D/c Line (80ckm) | 48.26 |  |  |  |  | 20 | 28.26 | [5 empty] | 48.26
13 | i. Establishment of New 132/33 kV, 2x80 MVA at Sonahatu | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
14 | ii. Tamar – Sonahatu 132 kV Panther D/c Line (60ckm) | 36.19 |  |  |  |  | 20 | 16.19 | [5 empty] | 36.19
15 | iii. Silli – Sonahatu 132 kV Panther D/c Line (90ckm) | 54.29 |  |  |  |  | 20 | 34.29 | [5 empty] | 54.29
16 | i. Establishment of New 132/33 kV, 2x80 MVA at Dus Mile Ring Road | 74.95 |  |  |  |  | 40 | 34.95 |  |  |  |  | 74.95
17 | ii. Sarwal – Dus Mile Ring Road 132 kV Panther D/c Line (50ckm) | 30.16 |  |  |  |  | 10 | 20.16 |  |  |  |  | 30.16
18 | i. Establishment of New 400/132/33 kV, 2x315+2x80 MVA at Vikas with 2x80 MVAr bus reactor and provision for creation of 220 kV level in future | 260.51 |  |  | 100 | 160.51 | [5 empty] | 260.51
19 | ii. LILO of PVUNL – Chandil New 400 kV Quad moose D/c line at Vikas (30ckm) | 57.15 |  |  | 20 | 37.15 | [5 empty] | 57.15
20 | iii. LILO of Irba – Angada 132 kV panther D/c Line at Vikas (48ckm) iv. LILO point at Angada side to Vikas section of line with high capacity conductor v. Reconductoring of Angada to LILO point with high capacity conductor | 91.878 |  |  | 40 | 51.878 | [5 empty] | 91.878
21 | i. Establishment of New 400/220 kV, 2x500 MVA at Dumka with 2x80 MVAr bus reactor | 256.901 |  |  | 50 | 100 | 106.901 | [5 empty] | 256.901
22 | ii. Dumka (New) – Koderma 400 kV Quad Moose D/c Line (360ckm) | 685.8 |  |  | 200 | 200 | 285.8 | [5 empty] | 685.8
23 | iii. Shifting of Madanpur – Godda 220 kV Zebra D/c Line to Dumka(New) (04 ckm) | 2.95 |  |  |  |  | 2.95 | [5 empty] | 2.95
24 | iv. Dumka (New) – Madanpur 220 kV Twin Moose D/c Line (04 ckm) | 6 |  |  |  |  | 6 | [5 empty] | 6
25 | i. Establishment of New 220/132/33 kV, 2x200 + 2x80 MVA at Barharwa | 138.66 |  |  |  | 50 | 88.66 | [5 empty] | 138.66
26 | ii. LILO of one ckt of Godda – Lalmatia 220 kV D/c line at Barharwa(140 ckm) | 84.455 |  |  |  | 50 | 34.455 | [5 empty] | 84.455
27 | iii. LILO of Pakur – Rajmahal 132 kV Panther S/c line at Barharwa (20 ckm) | 12.06 |  |  |  |  | 12.06 | [5 empty] | 12.06
28 | iv. Barharwa – Barhait 132 kV Panther D/c Line (40 ckm) | 24.13 |  |  |  |  | 24.13 | [5 empty] | 24.13
29 | i. Establishment of New 220/132/33 kV, 2x200+2x80 MVA at Dobo Kapali | 138.66 |  |  |  | 50 | 88.66 | [5 empty] | 138.66
30 | ii. Dobo – Jamshedpur PG New 220 kV Zebra D/c Line (100 ckm) | 73.7 |  |  |  | 40 | 33.7 | [5 empty] | 73.7
31 | iii. Dobo – Kandra 132 kV Panther D/c Line (50 ckm) | 30.16 |  |  |  | 10 | 20.16 | [5 empty] | 30.16
32 | i. Establishment of New 132/33 kV, 2x80 MVA at Nimdih | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
33 | ii. Chandil(Old) – Nimdih 132 kV Panther D/c Line (100ckm) | 60.32 |  |  |  |  | 20 | 40.32 | [5 empty] | 60.32
34 | i. Establishment of New 132/33 kV, 2x80 MVA at Kanderbera | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
35 | ii. Kanderbera – Dobo 132 kV Panther D/c Line (50 ckm) | 30.16 |  |  |  |  | 10 | 20.16 | [5 empty] | 30.16
36 | i. Establishment of New 220/132/33 kV, 2x200+2x80 MVA at Bahragoda New | 138.66 |  |  |  | 50 | 88.66 | [5 empty] | 138.66
37 | ii. Bahragoda New – Jamshedpur New PG 220kV Zebra D/c Line (200 ckm) | 147.4 |  |  |  | 50 | 97.4 | [5 empty] | 147.4
38 | iii. LILO of Surda – Bahragoda 132 kV D/c Panther Line (80ckm) | 24.13 |  |  |  | 10 | 14.13 | [5 empty] | 24.13
39 | i. Establishment of New 132/33 kV, 2x80 MVA at Netarhat | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
40 | ii. Mahuadanr – Netarhat 132 kV Panther D/c Line (80ckm) | 48.26 |  |  |  |  | 20 | 28.26 | [5 empty] | 48.26
41 | i. Establishment of New 132/33 kV, 2x80 MVA at Katkamsandi | 74.95 | [5 empty] | 40 | 34.95 | [5 empty] | 74.95
42 | ii. Hazaribagh – Katkamsandi 132 kV Panther D/c Line (90ckm) | 54.29 | [5 empty] | 20 | 34.29 | [5 empty] | 54.29
43 | i. Establishment of New 132/33 kV, 3x80 MVA S/s at Ghato | 112.42 | [5 empty] | 20 | 20
44 | ii. LILO of Ramgarh – Hazaribagh 132 kV D/c line at Ghato S/s (50 ckm) | 60 | [5 empty] | 10 | 10
45 | i. Establishment of New 132/33 kV, 2x80 MVA at Dumri | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
46 | ii. Giridih – Dumri 132 kV Panther D/c Line (100 ckm) | 60.33 |  |  |  |  | 20 | 40.33 | [5 empty] | 60.33
47 | i. Establishment of New 132/33 kV, 2x80 MVA at Chakradharpur (Toklo Road) | 74.95 |  |  |  | 40 | 34.95 | [5 empty] | 74.95
48 | ii. LILO of Rajkharsawan – Chakradharpur(old) 132 kV Panther D/c line at Chakradharpur (Toklo Road) (10ckm) | 6.03 |  |  |  |  | 6.03 | [5 empty] | 6.03
49 | i. Establishment of New 132/33 kV, 2x80 MVA at Parsa(Manjhgoan) | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
50 | ii. Parsa – Noamundi 132 kV Panther D/c line(92ckm) | 55.5 |  |  |  |  | 20 | 35.5 | [5 empty] | 55.5
51 | i. Establishment of New 132/33 kV, 2x80 MVA at Solegundi(Bandga on) | 74.95 |  |  |  |  | 40 | 34.95 | [5 empty] | 74.95
52 | ii. Solegundi(Bandgao n) – khunti 132 kV Panther D/c line (70ckm) | 42.23 |  |  |  |  | 20 | 22.23 | [5 empty] | 42.23
53 | i. Establishment of New 220/132/33 kV, 2x200+2x80 MVA at Tantnagar | 138.66 |  |  |  |  | 50 | 88.66 | [5 empty] | 138.66
54 | ii. Tantnagar – Chaibasa PG 220 kV Panther D/c line (80ckm) | 58.96 |  |  |  |  | 20 | 38.96 | [5 empty] | 58.96
55 | iii. Parsa – Tantnagar 132 kV Panther D/c line(80ckm) | 48.26 |  |  |  |  | 20 | 28.26 | [5 empty] | 48.26
56 | i. Establishment of New 132/33 kV, 2x80 MVA at Duguni | 74.95 |  |  |  | 40 | 34.95 | [5 empty] | 74.95
57 | ii. Duguni – Tantnagar 132 kV Panther D/c line(90ckm) | 54.29 |  |  |  | 20 | 34.29 | [5 empty] | 54.29
58 | i. Establishment of Saria (New) 220/132/33 kV S/s with 2x200 MVA + 2x80 MVA ICT | 138.66 |  |  |  |  | 50 | 88.66 | [5 empty] | 138.66
59 | ii. Koderma – Saria (New) 220 kV D/c line (140 ckm) | 84.455 |  |  |  |  | 40 | 44.455 | [5 empty] | 84.455
60 | iii. Saria (New) – Saria 132 kV D/c line (10 ckm) | 6.032 | [5 empty] | 6.032 | [5 empty] | 6.032
61 | LILO of Golmuri – Jadugoda (Old) 132 kV Panther D/c Line at Jadugoda (New) (25 km) | 30.16 |  |  |  |  | 10 | 20.16 |  |  |  |  | 30.16
62 | Shifting of Hatia-I – Patratu (Old) 132 kV Panther D/c Line at Patratu (New) (06 km) | 7.24 |  |  |  |  | 7.24 |  |  |  |  | 7.24
63 | Shifting of DVC – Patratu (Old) 132 kV Panther D/c Line at Patratu (New) (06 km) | 7.24 |  |  |  |  | 7.24 |  |  |  |  | 7.24
64 | TTPS – Koderma 400 kV Quad Moose D/c Line (111 km) | 422.91 |  |  |  |  | 200 | 222.91 | [5 empty] | 422.91
65 | Shifting of Lohardaga (Old) – Gumla 132 kV Panther D/c Line at Lohardaga (New) (06 km) | 7.24 |  |  |  | 7.24 | [5 empty] | 7.24
66 | Hatia I – Hatia II ckt-3 132 kV Twin Zebra S/c line(0.05 km) | 0.13 |  |  |  | 0.13 | [5 empty] | 0.13
67 | Tamar – Chandil Panther S/c Line(38 km) | 98.04 |  |  |  |  | 50 | 48.04 | [5 empty] | 98.04
68 | Chandil – Manique 132 kV Panther S/c line(0.5 km) | 1.29 | [5 empty] | 1.29 | [5 empty] | 1.29
69 | Chandil – Adityapur 132 kV Panther S/c line(19 km) | 49.02 |  |  |  |  | 20 | 29.02 | [5 empty] | 49.02
70 | Japla – Sonenagar 132 kV Panther S/c line(20 km) | 51.6 | [5 empty] | 20 | 31.6 | [5 empty] | 51.6
71 | Deoghar – Jasidih 132 kV Panther D/C line(4 km) | 10.32 | [6 empty] | 10.32 | [5 empty] | 10.32
72 | Kendposi – Noamundi 132 kV Panther S/c line(26 km) | 67.08 | [5 empty] | 20 | 47.08 | [5 empty] | 67.08
73 | Kendposi – Chaibasa(old) 132 kV Panther S/c line(40.5 km) | 104.49 | [5 empty] | 50 | 54.49 | [5 empty] | 104.49
74 | Rajkharsawan – Chaibasa(old) 132 kV Panther S/c line(20 km) | 51.6 | [5 empty] | 20 | 31.6 | [5 empty] | 51.6
75 | Design, Engineering, Supply, Erection, Testing and Commissioning of LILO of one circuit from 220 KV TTPS - Govindpur Transmission Line at Maithon GSS (40 Km). | 162.1539 |  | 10 | 50 | 102.1539 | [5 empty] | 162.1539
76 | Design, Engineering, Supply, Erection, Testing and Commissioning of Construction Of 220 kV Double Circuit Baliapur To Maithon Transmission Line. (Line Length 36.30 Km) . | 165.2904 |  | 10 | 50 | 105.2904 | [5 empty] | 165.2904
77 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Baliyapur-SindriTransmission Line (16.00 KM). | 62.3834 |  | 5 | 20 | 37.3834 | [5 empty] | 62.3834
78 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Chandankiyari - ITI More, Chas Transmission Line (20.5 KM). | 72.8158 |  | 5 | 40 | 27.8158 | [5 empty] | 72.8158
79 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Dugda - ITI More, Chas Transmission Line (20 KM). | 78.0125 |  | 5 | 40 | 33.0125 | [5 empty] | 78.0125
80 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Maithon - Tundi Transmission Line (44.5 KM). | 117.5402 |  | 10 | 50 | 57.5402 | [5 empty] | 117.5402
81 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132/33 KV, 2 x 80 MVA Grid sub-station including construction of Control Room Building & approach road as well as other civil works at Sindri. | 72.778 |  | 5 | 40 | 27.778 | [5 empty] | 72.778
82 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132/33 KV, 2 x 80 MVA Grid sub-station including construction of Control Room Building & approach road as well as other civil works at ITI more Chas. | 72.778 |  | 5 | 40 | 27.778 | [5 empty] | 72.778
83 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132/33 KV, 2 x 80 MVA Grid sub-station including construction of Control Room Building & approach road as well as other civil works at Tundi | 72.778 |  | 5 | 40 | 27.778 | [5 empty] | 72.778
84 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132/33 KV, 2 x 80 MVA GIS Sub-Station including approach road as well as other civil works near Binod Bihari Chowk. | 110.1475 |  | 10 | 50 | 50.1475 | [5 empty] | 110.1475
85 | Design, Engineering, Supply, Erection, Testing and Commissioning of 220/132/33 kV, 2 x 200 + 2 x 80 MVA GIS Sub-Station including construction of Control Room Building & approach road as well as other civil works at Maithon (near Sanjay Chowk). | 167.8619 |  | 10 | 100 | 57.8619 | [5 empty] | 167.8619
86 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Maithon - Binod Bihari Chowk Transmission Line (58 KM). | 165.4123 |  | 10 | 100 | 55.4123 | [5 empty] | 165.4123
87 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Mahuda - Binod Bihari Chowk Transmission Line (19 KM). | 79.3513 |  | 5 | 40 | 34.3513 | [5 empty] | 79.3513
88 | Design, Engineering, Supply, Erection, Testing and Commissioning of LILO of one circuit from 132 KV D/C Chandankiyari - Govindpur Transmission Line at GSS Sindri (19 KM). | 72.4938 |  | 5 | 40 | 27.4938 | [5 empty] | 72.4938
89 | Design, Engineering, Supply, Erection, Testing and Commissioning of 132 KV DC Baliyapur - Tundi Transmission Line (38 KM). | 145.9177 |  | 10 | 100 | 35.9177 | [5 empty] | 145.9177
| Total | 7652.4656 | 0 |  | 1540.032 | 2135.9706 | 2063.016 | 1416.697 | 274.33 | 0 | 0 | 2785.4826 | 2198.806 | 2081.427 | 414.33

## Augmentation
Augmentation Schemes
Sl No. | Project | Estimated Amount (in Cr.) | Capital Expenditure Schedule | [5 empty] | Capitalization Schedule
|  |  | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31 | FY 2025-26 | FY 2026-27 | FY 2027-28 | FY 2028-29 | FY 2029-30 | FY 2030-31
1 | Augmentation of transformer capacity by replacement of 1x50 MVA ICT with 1x80 MVA at 132/33 kV Hatia- 1 S/s | 10.02 |  |  | 10.02 | [5 empty] | 10.02
2 | Augmentation of transformer capacity by replacement of 3x150 MVA ICT with 3x200 MVA & 1x200 MVA will be added at Hatia-II S/s | 62.51 |  |  | 20 | 42.51 | [5 empty] | 62.51
3 | Augmentation of transformer capacity by replacement of 1x50 MVA ICT with 1x80 MVA at 132/33 kV Namkum S/s | 10.02 |  |  | 10.02 | [5 empty] | 10.02
4 | Augmentation of transformer capacity by addition of 1x80 MVA ICT at 132/33 kV Kanke S/s | 9.72 |  |  |  | 9.72 | [5 empty] | 9.72
5 | Augmentation of transformer capacity by addition of 1x80 MVA ICT at 132/33 kV Lohardaga S/s | 9.72 |  |  |  |  | 9.72 | [5 empty] | 9.72
6 | Augmentation of transformer capacity by addition of 1x80 MVA ICT at 132/33 kV Tamar S/s | 9.72 |  |  |  |  | 9.72 | [5 empty] | 9.72
7 | Augmentation of transformer capacity by replacement of 2x50 MVA ICT with 2x100 MVA at 132/33 kV Pakur S/s | 27.34 |  | 10 | 17.34 | [5 empty] | 27.34
8 | Augmentation of transformer capacity by addition of 1x80 MVA ICT at 132/33 kV Sahebganj S/s | 9.72 |  |  |  | 9.72 | [5 empty] | 9.72
9 | Augmentation of transformer capacity by addition of 1x80 MVA ICT at 132/33 kV Rajmahal S/s | 9.72 |  |  |  | 9.72 | [5 empty] | 9.72
10 | Augmentation of transformer capacity by replacement of 2x50 MVA with 2x80 MVA ICT at 220/132/33 kV Godda S/s | 20.04 |  |  |  | 10 | 10.04 | [5 empty] | 20.04
11 | Augmentation of transformer capacity by replacement of 1x100 MVA with 1x200 MVA ICT & 1x20 MVA with 1x 80 MVA & further addition of 1x200 MVA at 220/132/33 kV Lalmatia S/s | 41.13 |  | 10 | 31.13 | [5 empty] | 41.13
12 | Augmentation of transformer capacity by replacement of 4x100 MVA with 4x200 MVA ICT at 220/132 kV Chandil(old) S/s | 62.8 |  |  |  | 20 | 42.8 | [5 empty] | 62.8
13 | Augmentation of transformer capacity by replacement of 4x50 MVA with 4x80 MVA ICT at 132/33 kV Adityapur- 1 S/s | 40.08 |  |  | 20 | 20.08 | [5 empty] | 40.08
14 | Augmentation of transformer capacity by replacement of 3x50 MVA with 3x100 MVA ICT at 132/33 kV Golmuri S/s | 41.01 |  |  | 20 | 21.01 | [5 empty] | 41.01
15 | Augmentation of transformer capacity by replacement of 1x20 MVA with 1x80 MVA ICT at 132/33 kV Jadugoda S/s | 10.02 |  |  |  |  | 10.02 | [5 empty] | 10.02
16 | Augmentation of transformer capacity by addition of 1x80 MVA at 132/33 kV Surda S/s | 9.72 | [5 empty] | 5
17 | Augmentation of transformer capacity by replacement of 2x20 MVA with 2x80 MVA ICT at 132/33 kV Japla S/s | 20.04 |  |  |  | 10 | 10.04 | [5 empty] | 20.04
18 | Augmentation of transformer capacity by addition of 1x200MVA at 220/132 kV Garhwa New(Bhagodih) S/s | 15.7 |  |  |  | 10 | 5.7 | [5 empty] | 15.7
19 | Augmentation of transformer capacity by addition of 1x500 MVA at 400/220 kV Latehar(New) S/s | 15.7 |  |  |  |  | 10 | 5.7 | [5 empty] | 15.7
20 | Augmentation of transformer capacity by replacement of 2x50 MVA with 2x80 MVA ICT at 132/33 kV Itkhori(Chatra) S/s | 20.04 |  |  |  |  | 10 | 10.04 | [5 empty] | 20.04
21 | Augmentation of transformer capacity by addition of 1x80 MVA at 132/33 kV Saria S/s | 10.02 |  |  |  | 10.02 | [5 empty] | 10.02
22 | Augmentation of transformer capacity by addition of 1x500 MVA at 400/220 kV Patratu New S/s | 33.24 |  |  |  | 10 | 23.24 | [5 empty] | 33.24
23 | Augmentation of transformer capacity by replacement of 2x50MVA with 2x100 MVA at 220/132/33 kV Extension of Patratu New S/s | 27.34 | [5 empty] | 10
24 | Augmentation of transformer capacity by addition of 1x80 MVA at 400/220/132/33 kV Koderma S/s | 9.72 | [5 empty] | 5
25 | Augmentation of transformer capacity by addition of 1x80 MVA at 220/132/33 kV Hazaribag S/s | 9.72 | [5 empty] | 5
26 | Augmentation of transformer capacity by replacement of 2x150MVA with 2x200 MVA + Augmentation of transformer capacity by addition of 1x200MVA & replacement of 2x50MVA with 2x100 MVA at 220/132/33 kV Extension of Jasidih S/s | 58.74 |  |  |  | 20 | 38.74 | [5 empty] | 58.74
27 | Augmentation of transformer capacity by addition of 1x80 MVA at 220/132/33 kV Giridih S/s | 9.72 |  |  |  |  | 9.72 | [5 empty] | 9.72
28 | Augmentation of transformer capacity by addition of 1x80 MVA at 132/33 kV Jamua S/s | 9.72 |  |  |  | 9.72 | [5 empty] | 9.72
29 | Augmentation of transformer capacity by replacement of 1x20MVA with 1x80 MVA at 132/33 kV Jamtara S/s | 10.02 |  |  | 10.02 | [5 empty] | 10.02
30 | Augmentation of transformer capacity by replacement of 1x20 MVA with 1x80 MVA at 132/33 kV Chitra S/s | 10.02 |  |  |  | 10.02 | [5 empty] | 10.02
31 | Augmentation of transformer capacity by replacement of 2x20 MVA with 2x50 MVA at 132/33 kV Chakradharpur Old S/s | 11.5 |  |  |  |  | 11.5 | [5 empty] | 11.5
32 | Augmentation of transformer capacity by replacement of 2x20 MVA with 2x80 MVA at 132/33 kV Kendposi S/s | 20.04 |  |  |  | 10 | 10.04 | [5 empty] | 20.04
33 | Augmentation of transformer capacity by replacement of 2x20 MVA with 2x80 MVA at 132/33 kV Goelkera S/s | 20.04 |  |  |  | 10 | 10.04 | [5 empty] | 20.04
34 | Augmentation of transformer capacity by replacement of 1x25 MVA with 1x80 MVA at 132/33 kV Chaibasa(old) S/s | 10.02 |  |  |  |  | 10.02 | [5 empty] | 10.02
35 | Augmentation of transformer capacity by replacement of 2x150 MVA with 2x200 MVA & addition of 1x200 MVA at 220/132/33 kV Chaibasa New(Ulijhari) S/s | 41.7 |  |  |  | 20 | 21.7 | [5 empty] | 41.7
| Total | 746.33 | 0 | 20 | 138.53 | 262.52 | 253.04 | 40.74 | 0 | 0 | 98.53 | 202.52 | 353.04 | 35.74